Scrum - Rituals Workbook

Iterative Time-box Activities

Analyze

Design

Construct

Integrate

Test

Quality of an Iteration

Determined based off of different factors like the ability to deliver value, the efficiency of the process, and the effectiveness of the team’s collaboration

Quality of Outcome Determination

Determined by the effectiveness of the time boxed iterations.

Sprint definition Known as the heart of scrum, typically a fixed period of time in which a team will commit to delivering a set of features/improvements.

Determination of length of sprint. One month or less/2-4 weeks, but determined based on a team’s belief of what would work best to enhance team productivity.

Sprint Rituals

| Sprint Planning Meeting | Consists of the initial inputs of Sprint planning including what is the Definition of Done, the Product Backlog, Retrospective commitments, and the Dev team. During the meeting, a sprint goal is established along with a plan for the delivery that needs to get done. In the end, the Spring Goal, Sprint Forecast, and Sprint Backlog are finalized. |
| --- | --- |
| Estimation | The act of determining (guessing) the expected size of something. In Scrum, estimating helps to set expectations as to the amount of work that can be performed or the length of time until something is finished. |

3 types of estimation 			When this occurs 		Unit of measure

| Portfolio Backlog | Portfolio Planning | T-shirt sizes |
| --- | --- | --- |
| Product Backlog | Product Backlog Grooming | Story points / ideal days |
| Sprint Backlog Tasks | Sprint Planning | Ideal hours / effort hours |

Scrum Roles Involved in Estimation

Planning Poker							 Triangulation

Ideal day / Ideal hour Ideal hour: Focus on the task; no interruptions Ideal day: Constantly able to focus; No interruptions

Problems with Ideal estimation There can’t be any interruptions as the team as to maintain full focus on the tasks

Daily Standup

Purpose Meant to address the general progression of a sprint/what work is getting done and to address any blockers

3 Questions What have you do since the last meeting? What are you planning to do before the next meeting? Do you experience any obstacles?

Rules Must be within 15 minutes, should occur at the same time and place to make a routine, people should be standing during the meeting, and to address the 3 main questions. Adapt the plan for the next 24 hours to ensure that we move forward toward a successful increment.

Pair Programming

Collective code ownership! All team members understand the code. Two team members; one task. Driver and navigator. Constant reflection (real-time reviewing). Reduction of noise.

Sprint Review Meeting

Purpose Meant to talk about the story of the journey and give feedback, demo meeting and informal

Participants The scrum team, stakeholders are invited, the product owner and the scrum master.

Timing 4 hours max

Location Typically a meeting space within the organization - might be the same place as other meetings

Expected Outcomes Meant for feedback, and collaboration. Talk about story

Sprint Retrospective Meeting

Last activity in sprint

3 hours max

Reflect on sprint

Improvements of process for future

Review the “Definition of Done”

Ritual Timing

| Sprint Duration | 1 month |
| --- | --- |
| Daily Stand-up | 15 minutes |
| Spring Planning | 8 hours |
| Spring Review | 4 hours |
| Sprint Retrospective | 3 hours |